## Features
| Important | Time requirement | Completion
Home page | Required
Search | Required
About us | Required
How it works | Required
Form | Required
Search results | Required
Front end | Required
Database | Required
Product profile | Required
Front end | Required
Upload additional information | Required
Stored somewhere | Required
Profile creation and log-in | Required
Forms | Required
Database | Required
Communication | Optional
Messaging | Optional
Book a call | Optional
Calculators | Optional
Blog | Optional

## Sheet4
Investor/owner | Max LVR | Loan size min | Loan size max | Fixed or variable interest | Offset | Redraw | Extra repay | Interest only | Full doc/low doc/no doc | Product name | Product description | Bank | Setup costs | Ongoing costs | Comparison rate | Advertised rate
Investor | 80% | 100000 | 500000 | Variable | 1 | 1 | 1 | 1 | Full doc | Standard Home Loan |  | CBA | 500 | 500 | 4.5% | 4.4%
|  | Nullable | Nullable | [7 empty] | Nullable
Question | Affected columns
Refinance/buy | None
Purchase price/property worth | LVR, loan size min, loan size max
Deposit/Loan amount
Best situation | None
How will property be used | Investor/owner
How would you like to repay | Interest only
Current credit history | None
Employment type | Full doc/low doc | Employee or self-employ with at least two years of documents = full doc
2 years of Tax Returns
Important features | Offset, redraw, bank (major lender)
Dropdowns
bank description
remove features to keep only 3

## Design to dos
Location | Change
Navbar | Logo, icons | Logo idea: door opening
Home page button icons | Update icons
Footer | Logo, sections
Home | How it works, 3 icons. Find example
whyRefinance | Colours after clicking options
Form | 1) Refi or new purchase 2) Questions required for loan amount and LVR 3) Investment or live 4) Low/nodoc
Product | Remove total loan amount and borrowing power column
Change view details to "apply now"
Remove star column
Remove compare loans button
Remove right hand panel
Update navbar
Update font and colours
Comparison rate!Monthly P&I repayments!Ongoing rate!Ongoing fees! Upfront fees!Apply now
Make dynamic (product name column wider, other columns narrower). Remove columns on smaller screens
Column headers
Update logos
Delete Show all lenders
Delete total loan term
Add 1st home buyers
add sql for refinance/ repayment freq
Instruction manual for MLB application portal

## Timeline
Week beginning
Action | 2017-12-26 | 2018-01-02 | 2018-01-09 | 2018-01-16 | 2018-01-23 | 2018-01-30 | 2018-02-06 | 2018-02-13 | 2018-02-20 | 2018-02-27 | 2018-03-06 | 2018-03-13 | 2018-03-20 | 2018-03-27 | 2018-04-03 | 2018-04-10 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08 | 2018-05-15 | 2018-05-22 | 2018-05-29
Search result working with dummy data
User login
Script for actual data
Refining first draft

## Hours worked
Day | Hours | Activities | Paid
29th Dec | 9 | Set up RDS, EC2, Elastic Beanstalk and Security Policies | Yes
Set up MySQL Workbench
PHP code to connect to RDS through EC2 and create/edit tables
30th Dec | 9 | AJAX integration, SQL functional dependencies and scripts | Yes
3rd Jan | 6 | Integration with Niraj's code, php PDO script for dynamic page | Yes
4th Jan | 8 | Set up dynamic values on the search page. | Yes
Dynamically linked product page to Search page using id
Update SQL query WHERE condition, add new SQL query for record count
5th Jan | 3 | Updated product page query and content. | Yes
7th Jan | 9 | Changed Backend Architecture from ajax to URL variables to include dropdowns | Yes
Added php backend and modified query for "I want to buy a home"option
Updated javascript validation errors
9th Jan | 9 | Updated dynamic dropdowns for: | Yes
Refinance/buy new
owner/investor
principal&interest/interest
offset/redraw
updated javascript function to show hide dropdowns
10th Jan | 10 | Redesigned Database. Added User tables. | Yes
Created login page and validation script
Dynamic css changes(select/unselect) to features on product and search page
21st Jan | 2 | Changes to customer table. Updated primary keys to optimize database. | Yes
28th Jan | 9 | Query to compare customer table with loan table and fetch products | Yes
Query and php script to insert customer details in customer table
changes to serach.php page to fetch dynamic records using new query
Update customer details script and php page
29th Jan | 5 | Added extra repay constraint to query and script | Yes
extended javascript for buying new home
date converstion code to store in sql (settlement date)
bug fixes in update customer details through dropdown menu
4th Feb | 8 | Scraping Analysis | Yes
5th Feb | 7 | Scraping Analysis | Yes
6th Feb | 1 | Scraping Analysis | Yes
7th Feb | 8 | Rate City scrape script | Yes
9th Feb | 8 | Data extraction from SQL (shell script)
SQL script: JSON to csv and Insert statements
11th Feb | 7 | SQL table restructuring and Query modifications
Bank Data SQL query dynamic construction
Product details SQL Insert Query dynamic construction
12th Feb | 6 | Feeding into Website
Bug fixes due to query changes
Modification to customer details query according to changes in product table
13th Feb | 4 | Comma separation dynamic
Variable/Fixed Rate query and dropdown code
14th Feb | 4 | Principal and Interest/Interest only query and dropdown code
Repayment Frequency Query and dropdown code
15th Feb | 6 | Format table/ Product name
Change logic to pick from product_id as primary key
Calculation for monthly ongoing fee
Format View product page
17th Feb | 8 | 1) Refi or new purchase 2) Questions required for loan amount and LVR 3) Investment or live 4) Low/nodoc
Remove total loan amount and borrowing power column
Change view details to "apply now"
18th Feb | 8 | Remove star column
Remove compare loans button
Comparison rate!Monthly P&I repayments!Ongoing rate!Ongoing fees! Upfront fees!Apply now
Column headers
19th Feb | 10 | Delete Show all lenders
Delete total loan term
Add 1st home buyers
add sql for refinance/ repayment freq
Update logos
Remove right hand panel
19th Feb | 3 | LOGO Design - Chaitrali
20th Feb | 7 | Sorting results of all columns, Monthly repayment calculations
Product page update discharge fee, ongoing fee, css/html changes
23rd Feb | 1 | LOGO Design - Chaitrali
23rd Feb | 2 | Header changes, 3 icons, colour changes, buttons/hover