## Features
| Important | Time requirement | Completion
Home page | Required
Search | Required
About us | Required
How it works | Required
Form | Required
Search results | Required
Front end | Required
Database | Required
Product profile | Required
Front end | Required
Upload additional information | Required
Stored somewhere | Required
Profile creation and log-in | Required
Forms | Required
Database | Required
Communication | Optional
Messaging | Optional
Book a call | Optional
Calculators | Optional
Blog | Optional

## Sheet4
Investor/owner | Max LVR | Loan size min | Loan size max | Fixed or variable interest | Offset | Redraw | Extra repay | Interest only | Full doc/low doc/no doc | Product name | Product description | Bank | Setup costs | Ongoing costs | Comparison rate | Advertised rate
Investor | 80% | 100000 | 500000 | Variable | 1 | 1 | 1 | 1 | Full doc | Standard Home Loan |  | CBA | 500 | 500 | 4.5% | 4.4%
|  | Nullable | Nullable | [7 empty] | Nullable
Question | Affected columns
Refinance/buy | None
Purchase price/property worth | LVR, loan size min, loan size max
Deposit/Loan amount
Best situation | None
How will property be used | Investor/owner
How would you like to repay | Interest only
Current credit history | None
Employment type | Full doc/low doc | Employee or self-employ with at least two years of documents = full doc
2 years of Tax Returns
Important features | Offset, redraw, bank (major lender)
Dropdowns
bank description
remove features to keep only 3

## Design to dos
Location | Change
Navbar | Logo, icons
Home page button icons | Update icons
Footer | Logo, sections
Home | How it works

## Timeline
Week beginning
Action | 2017-12-26 | 2018-01-02 | 2018-01-09 | 2018-01-16 | 2018-01-23 | 2018-01-30 | 2018-02-06 | 2018-02-13 | 2018-02-20 | 2018-02-27 | 2018-03-06 | 2018-03-13 | 2018-03-20 | 2018-03-27 | 2018-04-03 | 2018-04-10 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08 | 2018-05-15 | 2018-05-22 | 2018-05-29
Search result working with dummy data | bar: 2017-12-26 to 2018-01-02
User login | bar: 2018-01-09 to 2018-01-16
Script for actual data | bar: 2018-01-09 to 2018-01-16
Refining first draft | bar: 2018-01-23 to 2018-01-30

## Hours worked
Day | Hours | Activities | Paid
29th Dec | 9 | Set up RDS, EC2, Elastic Beanstalk and Security Policies | Yes
Set up MySQL Workbench
PHP code to connect to RDS through EC2 and create/edit tables
30th Dec | 9 | AJAX integration, SQL functional dependencies and scripts | Yes
3rd Jan | 6 | Integration with Niraj's code, php PDO script for dynamic page | Yes
4th Jan | 8 | Set up dynamic values on the search page. | Yes
Dynamically linked product page to Search page using id
Update SQL query WHERE condition, add new SQL query for record count
5th Jan | 3 | Updated product page query and content. | Yes
7th Jan | 9 | Changed Backend Architecture from ajax to URL variables to include dropdowns | Yes
Added php backend and modified query for "I want to buy a home"option
Updated javascript validation errors
9th Jan | 9 | Updated dynamic dropdowns for: | Yes
Refinance/buy new
owner/investor
principal&interest/interest
offset/redraw
updated javascript function to show hide dropdowns
10th Jan | 10 | Redesigned Database. Added User tables. | Yes
Created login page and validation script
Dynamic css changes(select/unselect) to features on product and search page