## Features
| Important | Time requirement | Completion
Home page | Required
Search | Required
About us | Required
How it works | Required
Form | Required
Search results | Required
Front end | Required
Database | Required
Product profile | Required
Front end | Required
Upload additional information | Required
Stored somewhere | Required
Profile creation and log-in | Required
Forms | Required
Database | Required
Communication | Optional
Messaging | Optional
Book a call | Optional
Calculators | Optional
Blog | Optional

## Sheet4
Investor/owner | Max LVR | Loan size min | Loan size max | Fixed or variable interest | Offset | Redraw | Extra repay | Interest only | Full doc/low doc/no doc | Product name | Product description | Bank | Setup costs | Ongoing costs | Comparison rate | Advertised rate
Investor | 80% | 100000 | 500000 | Variable | 1 | 1 | 1 | 1 | Full doc | Standard Home Loan |  | CBA | 500 | 500 | 4.5% | 4.4%
|  | Nullable | Nullable | [7 empty] | Nullable

## Timeline
Week beginning
Action | 2017-12-26 | 2018-01-02 | 2018-01-09 | 2018-01-16 | 2018-01-23 | 2018-01-30 | 2018-02-06 | 2018-02-13 | 2018-02-20 | 2018-02-27 | 2018-03-06 | 2018-03-13 | 2018-03-20 | 2018-03-27 | 2018-04-03 | 2018-04-10 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08 | 2018-05-15 | 2018-05-22 | 2018-05-29
Search result working with dummy data | bar: 2017-12-26 to 2018-01-02
User login | bar: 2018-01-09 to 2018-01-16
Script for actual data | bar: 2018-01-09 to 2018-01-16
Refining first draft | bar: 2018-01-23 to 2018-01-30

## Hours worked
Day | Hours | Activities
29th Dec | 9 | Set up RDS, EC2, Elastic Beanstalk and Security Policies
Set up MySQL Workbench
PHP code to connect to RDS through EC2 and create/edit tables